CSS-OPS-TRACK-001

Immediate Actions Tracker

| Document Reference | CSS-OPS-TRACK-001 |
| --- | --- |
| Version | 1.0 |
| Classification | INTERNAL — ALL TEAM |
| Author | Andy Jones, Steward |
| Date | 17 February 2026 |
| Review Cadence | Daily at 12:30 UK stand-up |
| Distribution | Andy (FULL), Steven (FULL), Chris (FULL), Tom (FULL), Blue (TASK) |

## TRACK 1: BUILD PLAN EXECUTION (CSS-OPS-DOC-002)

| # | Action | Owner | Deadline | Status |
| --- | --- | --- | --- | --- |
| 1.1 | Send Blue credentials + CSS-OPS-DOC-003 | Steven | 17 Feb | Done |
| 1.2 | Verify n8n trend scanner runs | Andy | 17 Feb | Done |
| 1.3 | Confirm Gumroad/Etsy accounts active | Andy/Steven | 17 Feb | Due today |
| 1.4 | Post Tenerife operator job spec | Chris | 18 Feb | Due tomorrow |
| 1.5 | Schedule Monday check-in with Blue | Steven | 18 Feb | Due tomorrow |
| 1.6 | Blue runs Monday routine | Blue | 24 Feb | Next week |
| 1.7 | First product listed | System | 24 Feb | Next week |

Critical path: 1.3 gates 1.7. No product listing without confirmed marketplace accounts.

## TRACK 2: SOVEREIGN COMMAND DECK (CSS-DECK-001)

| # | Action | Owner | Deadline | Status |
| --- | --- | --- | --- | --- |
| 2.1 | Create Notion/Google Sheets template from spec | Steven | 18 Feb | Due tomorrow |
| 2.2 | Share with Blue (edit), Andy/Chris (view) | Steven | 18 Feb | Due tomorrow |
| 2.3 | Blue enters first weekly entry | Blue | 23 Feb | Next week |
| 2.4 | Steven reviews and stores in Tresorit | Steven | 24 Feb | Next week |

## TRACK 3: PIOPL AGENT DEPLOYMENT (CSS-OPS-DOC-004)

| # | Action | Owner | Deadline | Status |
| --- | --- | --- | --- | --- |
| 3.1 | Build agent registry database (PostgreSQL) | Tom | 1 Mar | Not started |
| 3.2 | Extend SIP engine to support agent profiles | Andy+Claude | 15 Mar | Not started |
| 3.3 | Create first agent template (Dig. Prod. Gen.) | Andy | 15 Mar | Not started |
| 3.4 | Deploy first 10 agents to test pipeline | Tom | 1 Apr | Not started |
| 3.5 | Set up agent revenue ledger (Stripe Connect) | Steven | 1 Apr | Not started |
| 3.6 | Scale to 100 agents after validation | Tom+Blue | 1 May | Not started |

## TRACK 4: NODE-1 PHYSICAL SOVEREIGNTY

| # | Action | Owner | Deadline | Status |
| --- | --- | --- | --- | --- |
| 4.1 | ZEC company registration | Steven | 1 Mar | Not started |
| 4.2 | RIC investment reserve setup | Steven | 1 Mar | Not started |
| 4.3 | Hardware order (MVP EUR 26k config) | Andy/Steven | 5 Mar | Not started |
| 4.4 | Colo reservation (D-ALiX or Civicos) | Chris | 5 Mar | Not started |
| 4.5 | Tenerife operator start date | Chris | 24 Feb | Next week |

## TRACK 5: ENTERPRISE READINESS (CSS-OPS-DOC-003)

| # | Action | Owner | Deadline | Status |
| --- | --- | --- | --- | --- |
| 5.1 | Document frozen as canonical | Andy | 16 Feb | Done |
| 5.2 | Next profile test (scale test 1,000 hires) | Optional | TBD | On hold |
| 5.3 | Integrate with Node-1 for audit mirroring | Tom | Post-Node-1 | Future |

# 48-HOUR WINDOW — ACTIONS DUE BY 19 FEBRUARY 2026

| # | Action | Owner | Due | Escalation |
| --- | --- | --- | --- | --- |
| 1.3 | Confirm Gumroad/Etsy accounts active | Andy/Steven | 17 Feb | E1 at 21 Feb |
| 1.4 | Post Tenerife operator job spec | Chris | 18 Feb | E1 at 22 Feb |
| 1.5 | Schedule Monday check-in with Blue | Steven | 18 Feb | E1 at 22 Feb |
| 2.1 | Create Command Deck template | Steven | 18 Feb | E1 at 22 Feb |
| 2.2 | Share Command Deck with team | Steven | 18 Feb | E1 at 22 Feb |

PATTERN: 4 of 5 actions in the 48-hour window are Steven dependencies. If these slip, escalation ladder from CSS-OPS-DOC-006 activates automatically.

| STEWARD SIGN-OFF | DATE |
| --- | --- |
| Andy Jones | 17 February 2026 |